## Sheet1
No | Title | Task Description | MoSCow | Estimated Finish Date
1 | Dashboard | Need hyper link | S | Done
2 | Logo | Press on that to go home page | M | Done
3 | Customer | Need to add Customer ID | M | Done
|  | About more details should have beside of delete not at below of that | M | Done
|  | When finish the editing and then should go to view the edited session | S | Done
4 | Project | Need to separate the tab for details and see clearly | S | Done
|  | Should have log history for maintance | S | 23.8.2023 | done
|  | Should have project status | S | 24.8.2023 | done
|  | Should have project ID | S | 24.8.2023 | done
5 | User Permission | when edit the customer, one user have many customer | S | 25.8.2023 | done
6 | Module | Module can choose with specific project | S | 28.8.2023 | done
7 | Issue Type | Issue type should have specific ID | S | Done
8 | Assign Incident | After creating new incident the screen jump out to Incident start page | M | Done
|  | Attachment should have ID and display with ID when error occur | S | 29.8.2023
|  | when the status is change then assigned person disappear | M | Done
|  | Can't choose the assign person after assigned | S | Done
|  | Should have description why was assign | S | 29.8.2023 | done
|  | should have assigned logs and historys | S | 30.8.2023 | done
|  | In assign to me section, search bar will work with ID | M | Done
9 | Report | Should display the priority report of incident in dashboard | S | Done
10 | User | Technician should have job level and specific module | S | 31.8.2023 | done