## Sheet1
No | Title | Task Description | MoSCow |  | Estimated Finish Date
1 | Dashboard | Need hyper link | S |  | Done
2 | Logo | Press on that to go home page | M |  | Done
3 | Customer | Need to add Customer ID | M |  | Done
|  | About more details should have beside of delete not at below of that | M |  | Done
|  | When finish the editing and then should go to view the edited session | S |  | 16.8.2023 | done
4 | Project | Need to separate the tab for details and see clearly | S |  | 17.8.2023 | done
|  | Should have log history for maintance | S | migration | 18.8.2023 | last maintenance ko modify lote tt user twe ko swe htote pya (Reporting -> Report2 -> Last Maintenance Log History)
|  | Should have project status | S | migration | 18.8.2023 | need to add in create and edit page
|  | Should have project ID | S | migration | 18.8.2023 | need to show in edit page
5 | User Permission | when edit the customer, one user have many customer | S |  | 21.8.2023 | done | user details -> Edit -> Customer
6 | Module | Module can choose with specific project | S | migration | 21.8.2023
7 | Issue Type | Issue type should have specific ID | S |  | 21.8.2023 | done
8 | Assign Incident | After creating new incident the screen jump out to Incident start page | M |  | 22.8.2023 | done
|  | Attachment should have ID and display with ID when error occur | S |  | 23.8.2023 | already have, need to ask
|  | when the status is change then assigned person disappear | M |  | 24.8.2023 | done
|  | Can't choose the assign person after assigned | S |  | 25.8.2023 | done
|  | Should have description why was assign | S | migration | 25.8.2023 | In progress
|  | should have assigned logs and historys | S | migration | 28.8.2023
|  | In assign to me section, search bar will work with ID | M |  | 28.8.2023 | done
9 | Report | Should display the priority report of incident in dashboard | S |  | 29.8.2023 | done
10 | User | Technician should have job level and specific module | S | migration | 30.8.2023 | User -> edit/create -> job level